Dr. J. J. Magdum College of Engineering, Jaysingpur - 416 101**.**

Research and Development Cell

**U.G. Students Project Schedule**

|  |  |  |
| --- | --- | --- |
| **Sr. No.** | **Activity** | **Tentative date of every year** |
| **Semester - I** | | |
| 01 | Submission of project topic with names of group member | 1st of August |
| 02 | Finalization of topic and allotment of guide by department through DRC | 5th of August |
| 03 | Submission of synopsis duly signed by students and guide | 10th of August |
| 04 | Presentation of synopsis before DRC | 14th of August |
| 05 | Introduction and literature review presentation | 10th of September |
| 06 | Methodology and future work presentation | 30th of September |
| **Semester – II** | | |
| 07 | Progress presentation 1 | 30th of January |
| 08 | Progress presentation 2 | 28th of February |
| 09 | Final presentation before DRC along with submission of spiral bound copy | 30th of March |
| 10 | Checking of project format on spiral bound by Dean R & D | 5th of April |
| 11 | Submission of final bound copy | 10th of April |

**U.G. Students Project Marking Scheme**

|  |  |  |
| --- | --- | --- |
| **Sr. No.** | **Activity** | **Marks** |
| **Semester - I** | | |
| 01 | Submission of project topic with names of group member | A1 = 0.08 × TM1 |
| 02 | Submission of synopsis duly signed by students and guide | A2 = 0.08 × TM1 |
| 03 | Introduction and literature review presentation | A3 = 0.24 × TM1 |
| 04 | Methodology and future work presentation | A4 = 0.30 × TM1 |
| 05 | Guides mark | A5 = 0.30 × TM1 |
| **Semester – II** | | |
| 06 | Progress presentation 1 | A6 = 0.20 × TM2 |
| 07 | Progress presentation 2 | A7 = 0.20 × TM2 |
| 08 | Final presentation before DRC along with submission of spiral bound copy | A8 = 0.30 × TM2 |
| 09 | Guides mark | A9 = 0.30 × TM2 |

**Notes: -**

1. TM1 = Total term work marks allotted by SUK for project work in semester I.
2. TM2 = Total term work marks allotted by SUK for project work in semester II.
3. Distribution of marks is given in form of multiplying factor.
4. Round up or down the marks to get the whole number as per requirement.
5. In rubrics also distribution of marks is given in form of multiplying factor.

**U.G. Students Project Rubric for Marking Scheme of Semester - I**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Level** | **Unsatisfactory** | **Developing** | **Satisfactory** | **Excellent** |
| **Activity** |
| Submission of project topic with names of group member | Submitted after scheduled date.  (0.0 × A1) | Submitted on scheduled date, but without clear title.  (0.4 × A1) | Submitted before scheduled date with clear title.  (0.8 × A1) | Submitted well before scheduled date with research based title.  (1.0 × A1) |
| Submission of synopsis duly signed by students and guide | Submitted after scheduled date, copied topic.  (0.0 × A2) | Submitted on scheduled date, duly signed by group members and Guide. Copied topic but added own value.  (0.4 × A2) | Submitted before scheduled date duly signed by group members and Guide. Sufficient number of references. Filling gap of existing work. (0.8 × A2) | Submitted well before scheduled date duly signed by group members and Guide. Sufficient number of references. Innovative idea.  (1.0 × A2) |
| Introduction and Literature review presentation | Presented after scheduled date. No coordination between group members. No collection of literature.  (0.25 × A3) | Presented on scheduled date. Poor coordination between group members. Little collection of literature. (0.60 × A3) | Presented on scheduled date. Good coordination between group members. Sufficient collection of literature.  (0.85 × A3) | Presented on scheduled date. Excellent coordination between group members. Full collection of literature. Presented novel idea. (1 × A3) |
| **Level** | **Unsatisfactory** | **Developing** | **Satisfactory** | **Excellent** |
| **Activity** |
| Methodology and future work presentation | Presented after scheduled date. No coordination between group members. Little idea about methodology, future work and conclusion. (0.25 × A4) | Presented on scheduled date. Poor coordination between group members. Clear about methodology and future work, but no clear idea about conclusion.  (0.6 × A4) | Presented on scheduled date. Good coordination between group members. Clear about methodology, future work and conclusion.  (0.9 × A4) | Presented on scheduled date. Excellent coordination between group members. Clear about methodology and future work. Confident about conclusion.  (1 × A4) |
| Guides mark | Not reporting regularly. Reporting individually. Unable to explain.  (0.25 × A5) | Reporting regularly and in group. Partially explaining, need guides’ help.  (0.6 × A5) | Reporting regularly and in group. Fully explaining without guides’ help.  (0.9 × A5) | Reporting regularly and in group. Fully explaining with clear concepts.  (1 × A5) |

**U.G. Students Project Rubric for Marking Scheme of Semester - II**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Level** | **Unsatisfactory** | **Developing** | **Satisfactory** | **Excellent** |
| **Activity** |
| Progress presentation 1 | Presented after scheduled date. No coordination between group members. No progress.  (0.2 × A6) | Presented on scheduled date. Poor coordination between group members. Little progress.  (0.65 × A6) | Presented on scheduled date. Good coordination between group members. Satisfactory progress.  (0.9 × A6) | Presented on scheduled date. Excellent coordination between group members. Excellent progress.  (1 × A6) |
| Progress presentation 2 | Presented after scheduled date. No coordination between group members. No progress.  (0.2 × A7) | Presented on scheduled date. Poor coordination between group members. Little progress.  (0.65 × A7) | Presented on scheduled date. Good coordination between group members. Satisfactory progress.  (0.9 × A7) | Presented on scheduled date. Excellent coordination between group members. Excellent progress.  (1 × A7) |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Level** | **Unsatisfactory** | **Developing** | **Satisfactory** | **Excellent** |
| **Activity** |
| Final presentation before DRC along with submission of spiral bound copy | Presented after scheduled date. No coordination between group members. No submission of spiral bound. Lack of info. Poor format and poor grammar in presentation. Work done not as per submitted synopsis.  (0.25 × A8) | Presented on scheduled date. Poor coordination between group members. Submitted spiral bound. Little info. Poor format and poor grammar in presentation.  (0.7 × A8) | Presented on scheduled date. Good coordination between group members. Submitted spiral bound. Sufficient info. Perfect format, but poor grammar in presentation. (0.95 × A8) | Presented on scheduled date. Excellent coordination between group members. Submitted spiral bound. Lot of info. No mistake in presentation.  (1 × A8) |
| Guides mark | Not reporting regularly. Reporting individually. Unable to explain. Final bound submitted after scheduled date. (0.25 × A9) | Reporting regularly and in group. Partially explaining, need guides’ help. Final bound submitted on scheduled date.  (0.7 × A9) | Reporting regularly and in group. Fully explaining without guides’ help. Final bound submitted before scheduled date.  (0.95 × A9) | Reporting regularly and in group. Fully explaining with clear concepts. Final bound submitted well before scheduled date.  (1 × A9) |